## Strategic Risks Jan20
Appendix 2 - LCC Strategic Risk Register
Risk Register Owner: Andy Keeling, COO | [6 empty] | Date completed: 09.03.20
RISK What is the problem; what is the cause; what could go wrong? What is it that will prevent you from achieving your objectives? | CONSEQUENCE/EFFECT: What would occur as a result, how much of a problem would it be, to whom and why? | EXISTING ACTIONS/CONTROLS What are you doing to manage this risk now? | RISK SCORE WITH EXISTING MEASURES |  |  | RESPONSE STRATEGY / ACTION Select from the 4T's Tolerate, Treat, Transfer, Terminate | FURTHER MANAGEMENT ACTIONS/CONTROLS | TARGET SCORE WITH FURTHER ACTIONS/ CONTROLS REQUIRED |  |  | COST | RISK OWNER | TARGET DATE
|  |  | Impact | Probability | Risk |  |  | Impact | Probability | Risk
18. Coronavirus (SARS coronavirus-2 (SARS-CoV-2)) locally results in significant loss of staff at any one time and/or wider national measures designed to slow the spread of COVID-19 cause significant impacts on service delivery and the wider city | Council is unable to deliver any services including essential/critical services, or only deliver to a significantly reduced extent. Significant risk to the health, safety and welfare of vulnerable services users. Significant impacts on the local economy causing resulting impacts financially on the Council from reduced revenue including loss of income for commercially traded services. Reputational damage should the Council not be able to respond adequately | The Council has a corporate business continuity plan and arrangements and services each have their own business continuty plans. The corporate plan and arrangements have been invoked and all service areas are reviewing their business continuity plans in the light of this specific threat. A corporate business continuity major incident response group is meeting weekly to review the current situation and to identify actions and decisions needed to manage the response as well as determining what is needed in relation to internal and external communications. The Council is following closely the guidance provided by PHE and Government and sharing / promoting this as appropriate with key stakeholders eg schools, suppliers, staff, councillors and MPs etc. The Council is an active partner in the LRF arrangements and response. The LRF has established an SCG, TCG and Media and Comms Cell to support the response and the Council has representatives on each of those. The LRF is utilising established pandemic flu plans as a basis to guide the response where appropriate and has overall well rehearsed major incident arrangements in place. | 4 | 4 | 16 | Treat | Continue to utilise the corporate business continuity plan and incident response group to oversee and co-ordinate the Council's response taking into account the wider guidance from PHE and Govt. Continue to engage in the LRF response and act on guidance from PHE and Govt | 4 | 4 | 16 |  | Miranda Cannon / Ivan Browne | 31/05/20 and ongoing

## Process
IMPACT GRID:
LIKELIHOOD GRID:
Risk Response Strategies - The 4 T's
Risk response is the process of controlling identified risks. Risk response is a planning and decision making process whereby stakeholders decide how to deal with each risk. It may be worth bearing in mind that some risks could remain high even after being treated and hence not all risks are capable of being reduced. Where LCC have statutory responsibilities and the risk is still high with further control(s), it is advisable to treat it the best you can.
The following are the basic types of risk response:
Definitions of the 4T's
1. Tolerating Risk - This is where no action is taken to mitigate or reduce a risk. This may be because the cost of instituting risk reduction or mitigation activity is not cost-effective or the risks of impact are at so low that they are deemed acceptable to the business. A response is not warranted by the importance of the risk. If decided to tolerate the risk, you are agreeing to address the risk if and when it occurs (contingency plan/workaround reserve may be developed for this eventuality). Even when these risks are tolerated they should be monitored because future changes may make it no longer tolerable.
2. Treating Risk - This is a method of controlling risk through actions that reduce the likelihood of the risk occurring or minimise its impact prior to its occurrence. Also, there are contingent measures that can be developed to reduce the impact of an event once it has occurred. This will reduce the probability and/or impact of a risk (more effective than repairing the damage after the risk has occurred). This option requires resources and time - presenting a trade-off between doing nothing v the cost of mitigating the risk.
3. Transferring Risk - This is achieved through the use of various forms of insurance, or the payment to third parties who are prepared to take the risk on behalf of the organisation. Therefore, another party will be taking on the responsibility for its management and will bear the liability of the risk should it occur. The aim is that the risk is owned and managed by a third party best able to deal with it effectively. This method involves a premium and the cost effectiveness should be considered. Please note that transferring a risk to a third party can pose secondary risks, for example subcontracting.
4. Terminating Risk - This is the often ignored method for risk elimination. This can be done by altering an inherently risky process or practice to remove the risk. The same can be used when reviewing practices and processes in all areas of the business. If an item presents a risk and can be changed (by doing it another way and still achieving the objective) or removed without it materially affecting the business, then removing the risk should be considered; rather than attempting to Treat, Tolerate or Transfer it. However, not all risks can be avoided or eliminated and this approach may be a drain on resources.
The below is a step by step guide to assist in the completion of the Risk Assessment/Register form :
Steps for Template use:
1. The 'Business Objective' column should detail the project/initiative/service delivery you are risk assessing
2. Consider what will stop you from achieving the objective. Identify the risk(s) considering cause/risk/effect and possibly IF and THEN statements, articulate the risk(s) in the 'Risk' column
3. In the 'Consequence' column, state consequences/impacts/effect if risk were to materialise
4. Log the existing controls in the next column ('Existing Actions/Controls' column)
5. Having considered the existing controls in place, evaluate the risk (score the risk using the impact and likelihood table further below) and arrive at the current risk score
6. Decide whether the risk is acceptable i.e. Tolerate (see table on the right and below for possible actions to consider).
7. If it is acceptable, you simply monitor it from now on. If it’s not acceptable, you would possibly put in place further controls i.e. Treat. Select one of the 4'T's and log in next column. (THIS WOULD BE THE POINT TO CONSIDER WHETHER PRE-EXISTING CONTROLS THAT ARE BUILT INTO SYSTEM ARE WORKING SOUNDLY)
8. Log any further controls in the 'Further Management Actions' Column if they are required
9. Having considered the Further Management Action, re-evaluate the risk to arrive at the Target Risk Score
10. Cost of impact should cover cost of implementation of existing controls, any further controls and the impact cost, for example, you may need to source additional agency staff if key staff are on sick
11. It is crucial to identify an appropriate risk responder/actionee - the person who would be responsible for implementing the control(s).
12. It is also important to log a target date for reviewing the risk rather than putting down 'ongoing' as this could be easily missed.
13. When reviewing and monitoring your risk register/assessment, please consider the below:
- If and when any of the further controls are implemented, these become existing controls, therefore, transfer such controls to the current controls (once they are embedded and operating soundly)
- Further re-evaluate (the risk score with new existing controls) the risk where additional controls have been implemented
- Decide whether the risk is now acceptable with implementing further controls
Agree your risk assessment with your line manager.
The risk matrix below indicates where the identified risk would lie in the grid once scored.