## 29988
Date | Detials
2023-10-21 | Europools Notified immediately issue became apparent and they confirmed they would be on site on the 23rd.
2023-10-23 | Europools send report of their findings and chasing manufacturer on lead times of replacement hoses.
2023-10-23 | Site Management request quotes for Temporary repair to keep the pool operational and permanent repair.
2023-10-25 | Europools respond with quotes. Will be on site W/C 13th Nov to install temporary hoses. Moving works around to accommodate.
2023-10-27 | Leisure Facilities Devleopment Manager asks for quote for temp repair and then all work done in 12 weeks with permanent double braided hose.
2023-11-02 | Water Clarity Deterorates to unsafe levels. Decision to clsoe the pool is made. Europools confirm attendance of the Dive team to start the works 13th November as Divers and specialist equipment needs to be mobilised.
2023-11-13 | Europools attend site with dive team. Water clarity meant that deemed unsafe for them to carry out works in current conditions. Pool water samples taken to understand levels of contamination.
2023-11-22 | Site contacting Severn Trent for approval to dispose of pool water through trade effluent legislation as water is now suspected to be unsalvagable.
2023-11-29 | Confirmation from Severn Trent that the pool water would not be able to be dumped and would need to be removed by a waste disposal company with tankers.
2023-12-01 | Europools sourcing specialist contractors to remove pool water. Due to the amount of water and complexities Europools inform management they are unable to find a tanker company and are looking at alternative solution.
2023-12-14 | Ideal response (specialist in waste water removal) appointed by Europools work with Envronmental Agency and Severn Trent on a potential solution to pump the water into the sewers via a specailist filtration system.
2023-12-19 | Europools, ideal repsonse and Active Leicester management meet on site to discuss plan.
2023-12-19 | Europools, ideal repsonse and Active Leicester management meet on site to discuss plan to empty the pool and explain that this was reliant on outcomes of the water samples and a discharge consent being agreed by Severn Trent.
2024-01-08 | Water samples received and Ideal response and Site Management work on completing a temporary discharge trade effluent agreement.
2024-01-16 | Castle Water submit application and give reference number.
2024-01-17 | Site chase Severn Trent to ensure received application. Said it could take 60 days for a decision. Highlighted the priority of situation and they began looking at straight away. Advised it could be max of 5 working days as top priority now. Is with consultee team to ensure they have the capacity for us to dump volume of water needed.
2024-01-22 | Chase up call to Severn Trent for temporary trade effluent consent. Still with consultee team. They will make a few calls their end to try and get a response for us asap.
2024-01-24 | Severn Trent again chased for resolution on application consent.
2024-01-25 | Trade effluent consent granted but from 22nd-29th Jan. Ideal Response confrimed they would not be able to mobilise and complete works in timeframe given.
2024-01-25 | Ideal Response communicates with Severn Trent direct that he would need a week to mobilise and has requested dates changed to be from W/C 5th Feb.